## Summary
TTWF Portal — Manager Discussion & Bugs Backlog
Source: Point Discussed with Manager and Bugs.docx
Total items: 44 (13 changes + 31 bugs)
Live status tally
Not Started | 0
In Progress | 0
Blocked | 0
Done | 2
Verified | 35
Wont Fix | 7
Priority split
P0 | 9
P1 | 23
P2 | 12
Legend
Change | Behaviour / flow change agreed with manager
Bug | Regression or defect in current build
P0 | Critical — security / data leak / broken core
P1 | High — impacts workflow or UX materially
P2 | Medium — polish / minor improvement

## Backlog
ID | Type | Category | Title | Description (from doc) | Decision / Clarification | Proposed Fix | Priority | Status | Task ID (aitasks) | Notes | Updated On
BUG-01 | Bug | Role | Role maker applied directly without approval | On applying role maker to role, msg says 'sent for approval' but permission actually persists on role immediately (first create exception is OK, but subsequent updates must not apply until approval). | Update flow must keep Role.module_permissions untouched until approve; only payload stored in RoleRequest. | Audit RoleSerializer.update() for any direct write to module_permissions or approval_status on update. | P0 | Verified | TASK-059 | EditRole.jsx: pending payload prefill now gated on action_type=create. Update-pending shows approved snapshot. | 2026-04-15
BUG-02 | Bug | System | Emails are not being delivered | No emails going out (password notify, role approval, etc.) | Diagnose: Celery worker alive with pool=solo on Windows? DEFAULT_FROM_EMAIL set? SMTP credentials valid? Run a task manually, check logs. | Step 1 diag, step 2 fix whichever layer broken. | P0 | Verified | TASK-060 | CELERY_TASK_ALWAYS_EAGER=True when broker URL empty. DEFAULT_FROM_EMAIL added. Tasks now run in-process. | 2026-04-15
BUG-14 | Bug | Hierarchy | Hierarchy listing shows entries outside user access | Listing API returns all entries irrespective of user's M2M access. | Enforce access filter on every GET (not just when filter_access=true). Super admin / has_global_access bypass. | BaseGeoViewSet.get_queryset — always apply access filter unless global. | P0 | Verified | TASK-061 | Server-side fix in BaseGeoViewSet. Needs UAT test. | 2026-04-15
BUG-16 | Bug | Hierarchy | Cluster assigned to user still deletable | Soft delete should block if referenced in user access M2M. | BaseGeoViewSet.destroy: check access_{level} M2M count across users; block if > 0 with clear message. | Apply for country/province/district/area/cluster. | P0 | Verified | TASK-062 | Server-side fix in BaseGeoViewSet. Needs UAT test. | 2026-04-15
BUG-20 | Bug | Permissions | Holidays module in sidebar / accessible without permission | Sidebar shows Holidays even when user has no Holidays perm; URL accessible too. | Sidebar filter by user.permissions.holidays. Add Holidays to ROUTE_MODULE_MAP in withAuth. | Two-line fix + route guard. | P0 | Verified | TASK-063 | Drawer NAV_ITEM moduleCode added + withAuth route guard. | 2026-04-15
BUG-21 | Bug | Permissions | Donor add/edit buttons visible without permission | Even without donor.can_add/can_edit, UI shows the buttons. | Gate with authUser.permissions.donors in Donor pages. | Frontend condition per button/action. | P0 | Verified | TASK-064 | Donors.jsx gated Add button + DataTable isEditable/isDeletable by permissions. | 2026-04-15 | also check after deployement
BUG-22 | Bug | Permissions | User create URL accessible without users.can_add | Create User hidden from button but URL navigation still loads the page. | withAuth HOC: check can_add for create routes (separate module action map). | Extend ROUTE_MODULE_MAP to support action codes. | P0 | Verified | TASK-065 | withAuth ROUTE_MODULE_MAP upgraded to {module, action}. Create requires can_add, edit requires can_edit. | 2026-04-15
BUG-28 | Bug | Hierarchy | Dropdowns show hierarchy items not in user's access | Cascading dropdowns (CreateUser / HierarchyEdit) show entries user has no M2M to. | Use filter_access=true on dropdown-source endpoints. Backend already supports it; audit all callers. | Frontend caller audit + add flag. | P0 | Verified | TASK-066 | Server-side fix in BaseGeoViewSet. Needs UAT test. | 2026-04-15
BUG-29 | Bug | Auth | Deleted user still logged in on other browser | Soft delete doesn't invalidate active JWT. | Option A: token blacklist entry on soft-delete. Option B: JWT verification checks user.is_active + not deleted_at on each request. | Pick B (no extra storage) — custom AUTH_USER_MODEL JWT claim validation. | P0 | Done | TASK-067 | StrictJWTAuthentication + soft_delete mirrors is_active. Axios interceptor handles 401 codes. | 2026-04-15
CHG-01 | Change | Permissions | View auto-tick when Add/Edit/Delete ticked | If a user hasn't view permission, how we assign add/edit/delete (view must be included). | Auto-tick View on Add/Edit/Delete + backend validation rejects save if Add/Edit/Delete is true with View=false. | PermissionGrid onChange: auto-set view=true; untick of view auto-unticks a/e/d. Role serializer validate() enforces same. | P1 | Done | TASK-068 | PermissionGrid auto-link + backend validator. | 2026-04-15
CHG-03 | Change | User | User access: till cluster mandatory, school optional | All access levels till cluster mandatory; only school optional. | Validate on submit — cluster level at least one selection required (unless has_global_access). | FE yup schema + BE UserProfileSerializer validate(); scroll-to-error on first empty level. | P1 | Wont Fix | TASK-069 | Per-level validation country→cluster; BE mirrors. | 2026-04-15
CHG-04 | Change | User/Backend | Soft-deleted email & mobile reusable; employee_id globally unique | Re-create user with same email/mobile allowed if previous soft-deleted. Employee ID unique even across soft-deleted. | Partial unique index on email+mobile (WHERE deleted_at IS NULL). Employee ID stays full unique. | Migration drops existing unique constraints on email/mobile and adds partial unique indexes. Employee ID unchanged. | P1 | Verified | TASK-070 | soft_delete renames username/email/mobile with __deleted_<ts> suffix. | 2026-04-15
CHG-05 | Change | Role | Allow editing a pending role | Currently block. Allow — new request sent to checker; toast shows 'sent for approval'. | Remove the 400-block on PUT when pending exists; instead update the existing pending RoleRequest's payload (keep same request, overwrite payload). | Backend update() lifts the guard; updates latest pending RoleRequest.payload in place. Frontend EditRole stays the same. | P1 | Verified | TASK-071 | Pending RoleRequest overwritten in place instead of block. | 2026-04-15
CHG-07 | Change | Auth/User | Password validation rules everywhere | Min 8, 1 uppercase, 1 lowercase, 1 digit, 1 special — FE + BE. | Shared regex: ^(?=.*[a-z])(?=.*[A-Z])(?=.*\d)(?=.*[^\w\s]).{8,}$ | Create User, Edit User, MyProfile Change Password, forced change password, reset flow — all use shared validator. | P1 | Verified | TASK-072 | Shared Password validator (BE + FE) wired in all flows. | 2026-04-15
CHG-08 | Change | Hierarchy | Auto-assign created entity to creator's M2M | If user creates a hierarchy entity & has no global access, the new entity auto-adds to creator's M2M at that level. | BaseGeoViewSet.perform_create: if not has_global_access, add instance.id to profile.access_{level}. | One-line hook per viewset — skip if has_global_access=True. Do NOT touch parent entities. | P1 | Verified | TASK-073 | BaseGeoViewSet.perform_create auto-adds to creator M2M when not global. | 2026-04-15
CHG-09 | Change | Role | Request History tab + previous_payload tracking | On update reject: role stays Approved. Add 'Request History' tab showing all approved + rejected requests with diff (previous vs new). Approval Queue stays for pending only. | Add RoleRequest.previous_payload (JSON). On create/update: snapshot current Role state → previous_payload. UI tab lists done+rejected requests. | Migration + RoleRequestSerializer expose previous_payload + new endpoint /roles/{id}/history/ → filter requests by role & status in (approved, rejected). New Roles tab 'Request History'. | P1 | Verified | TASK-074 | RoleRequest.previous_payload + /roles/{id}/history/ + Request History tab. | 2026-04-15
CHG-10 | Change | User | Only approved roles in user role dropdown | Pending or Rejected roles must not appear in the role assign dropdown during Create/Edit user. | Roles API: add ?approved_only=true filter; frontend CreateUser/EditUser uses it. | RoleViewSet list filter + frontend query param. | P1 | Verified | TASK-075 | fetchRoles approvedOnly=true for user create/edit role dropdown. | 2026-04-15
CHG-11 | Change | User | Partial M2M save on edit user (scope-limited) | If LI user has fewer hierarchy levels than edited user, only mutate rows within LI's access set — preserve EU's extra access. | On PUT: diff submitted_ids vs existing_ids INTERSECTED with LI's access set; add/remove only within that intersection. Rows outside LI's set stay untouched. | UserProfileViewSet perform_update custom M2M merge. Unit-test the scope diff. | P1 | Verified | TASK-076 | _set_regional_access scoped=True: mutates only within LI scope. | 2026-04-15
BUG-04 | Bug | Role | Role checker: toggle logic for view permission | Role Checker toggled ON must auto-tick Roles can_view. In Edit Role, removing all Role perms still leaves checker set on users. | Auto-link in both create & edit; also: on role update approve, if module_permissions no longer includes Roles can_view, ensure any user checker-permission pivot is re-evaluated (server-side cleanup). | PermissionGrid logic + serializer post-save cleanup. | P1 | Verified | TASK-077 | PermissionGrid auto-link works in both create + edit flows. | 2026-04-15
BUG-06 | Bug | Auth | Inactive user login shows 'Invalid credentials' | Should show 'User is inactive, contact administrator'. | Check is_active before password check; return distinct error. | CustomTokenObtainPairSerializer.validate() — inspect user.is_active first. | P1 | Verified | TASK-078 | TokenObtainPairSerializer returns inactive_account code + message. | 2026-04-15
BUG-09 | Bug | Profile | Profile image uses localhost URL instead of UAT | Uploaded image returns http://localhost/media/... even on UAT. | Use request.build_absolute_uri(file.url) in serializer; configure MEDIA_URL to host-relative. | UserProfileSerializer profile_picture field method. | P1 | Verified | TASK-079 | profile_picture URL uses build_absolute_uri (non-localhost hosts only). | 2026-04-15
BUG-11 | Bug | Hierarchy | Cluster filter not filtering in listings | Cluster filter on hierarchy listing has no effect. | Verify query param 'cluster' is forwarded to /geo/hierarchy/ flat endpoint and filters by cluster_id. | HierarchyFlatView.get_queryset + frontend param. | P1 | Verified | TASK-080 | HierarchyFlatView accepts ?cluster param; FE forwards it. | 2026-04-15
BUG-13 | Bug | User | 'A user with this username already exists' shown for duplicate email | Backend error wording wrong. | Map serializer error 'username' → 'email' in response, or override the unique message. | UserProfileSerializer — set extra_kwargs error_messages on email. | P1 | Verified | TASK-081 | validate_username + validate_email map to email-worded error. | 2026-04-15
BUG-17 | Bug | Role | Edit role: remove all role perms, checker still assigned to user | Auto-untick Role Checker when Roles can_view goes off in Edit Role flow. | PermissionGrid: watch can_view toggle and untick role_checker. Already in create flow — port to edit. | Frontend only (logic fix). | P1 | Verified | TASK-082 | PermissionGrid cascade: roles.view OFF unticks role_checker. | 2026-04-15
BUG-18 | Bug | User | 'All' province select does not populate districts | On CreateUser cascading access, choosing All at Province level leaves districts empty. | CascadingAccessColumn: when All is picked, fetch districts for all selected provinces via batch call. | Frontend + ensure /users/all-access-tree already covers this. | P1 | Verified | TASK-083 | toggleAllForLevel fires per-item toggle to cascade fetch. | 2026-04-15
BUG-23 | Bug | Permissions | Real-time permission refresh on page refresh | After role update + approval, user's UI keeps old perms until logout. Should refresh on page refresh (no polling). | On app bootstrap: fire one GET /users/me/ after hydration; merge fresh permissions into Redux + localStorage. One call, not polling. | auth.slice bootstrap effect; skip if not authenticated. | P1 | Verified | TASK-084 | App.jsx bootstrap GET /users/me/ merges fresh permissions. | 2026-04-15
BUG-24 | Bug | User | Rejected role still appears in role dropdown | Tied to CHG-10 — enforce approved-only on role list consumed by CreateUser/EditUser. | Add approved_only query param. | Frontend + backend filter. | P1 | Verified | TASK-085 | Covered by CHG-10 approvedOnly filter. | 2026-04-15
BUG-26 | Bug | User | Case-sensitive email dedup — allows A@ vs a@ | Different casing passes unique check. | iexact check in serializer + case-insensitive unique index (lower(email)). | Migration: CREATE UNIQUE INDEX ... ON lower(email) WHERE deleted_at IS NULL. | P1 | Verified | TASK-086 | validate_email uses __iexact. | 2026-04-15
BUG-27 | Bug | Auth UI | Wrong current password: error not shown on screen | Error present in network tab but toast doesn't surface it. | ChangePassword.jsx: read err.response.data.detail and show toast. | Small frontend fix. | P1 | Verified | TASK-087 | ChangePassword.jsx maps detail current-password to field error. | 2026-04-15
BUG-30 | Bug | User | Global access user: entities not checked on edit | User has has_global_access=True but M2M is empty, so Edit page shows nothing ticked. | Frontend EditUser: if has_global_access, render every hierarchy node as checked & disabled. | No M2M write on save if global stays true. | P1 | Verified | TASK-088 | EditUser: global users auto-select all hierarchy via fetchAndSelectAll. | 2026-04-15
BUG-31 | Bug | User | Edit User page slow — too many API calls | Multiple calls on load. | Use /users/{id}/access-tree/ batch endpoint; remove redundant sub-calls. | Audit EditUser useEffect + helpers. | P1 | Wont Fix | TASK-089 | EditUser: loadUserAccess single batch call replaces cascading loop. | 2026-04-15
BUG-32 | Bug | User | No access level: no error shown, form does not submit | Silent failure — tied to CHG-03. | Show inline validation 'At least one cluster required' and scroll-to. | Covered by CHG-03. | P1 | Wont Fix | TASK-090 | Covered by CHG-03 per-level validation. | 2026-04-15
CHG-02 | Change | Hierarchy | Region create/edit: min district mandatory, area/cluster optional | Till district region assignation mandatory; area/cluster optional. On area change, region dropdown must NOT re-filter. | District = required. Area/Cluster = optional. Area change does not trigger region dropdown change in listing filters. | FE Region form validation + backend serializer validate_members(). Listing filter: area change leaves region dropdown untouched. | P2 | Wont Fix | TASK-091 | RegionSerializer requires district member. Area change already does not touch region dropdown. | 2026-04-15
CHG-06 | Change | User | Phone number validation — Pakistan format | Only 03 + 11 digits. Keyboard-level digits-only input. Error on submit (not inline) for length/format. | FE: onChange strips non-digits and caps length at 11. Submit check: ^03\d{9}$. BE validator mirrors. | TextBox gains inputMode='numeric' + digit-only filter. Serializer RegexValidator added. | P2 | Verified | TASK-092 | Phone field digits-only keyboard filter; ^03\d{9}$ on submit; backend validator mirrors. | 2026-04-15
CHG-12 | Change | User | Change password field on MyProfile — optional | Add New + Confirm password inputs on MyProfile. No 'current password' field. Blank = skip password update. | PUT /users/me/: if new_password present & confirm matches, validate via password rules, save hashed. Else skip. | MyProfile form: two optional fields, confirmed match validation, submit together with profile edit. | P2 | Verified | TASK-093 | MyProfile: optional New+Confirm password fields. Backend PUT /users/me/ accepts new_password. | 2026-04-15
CHG-13 | Change | Hierarchy | Searchable dropdowns on Hierarchy Edit only | Dropdowns in Hierarchy Edit page must be searchable (select2-style). Elsewhere unchanged. | Add `searchable` prop to existing Select component (client-side filter on options) — only enable on Hierarchy Edit page. | No new component required if prop-based; otherwise create SearchableSelect wrapper. | P2 | Verified | TASK-094 | Select gained searchable prop. HierarchySelector passes searchable in edit mode. | 2026-04-15
BUG-05 | Bug | User UI | Label styling mismatch (role, gender, status) | These 3 labels have different styling vs other labels on Create/Edit User. | Use shared Label component; unify font size/weight/colour. | Replace inline labels with <Label> component. | P2 | Verified | TASK-095 | Select label style unified with TextBox. Status/Flag Sync/Profile Picture labels migrated. | 2026-04-15
BUG-07 | Bug | User UI | Hierarchical label not clickable | Labels like country_name / province_name not clickable — only checkbox works. | Wrap in <label htmlFor={checkboxId}> instead of <span>. | CascadingAccessColumn component change. | P2 | Verified | TASK-096 | CascadingAccessColumn per-item row wrapped in <label> — text click toggles checkbox. | 2026-04-15
BUG-10 | Bug | Hierarchy UI | 'All Countrys' typo | Select placeholder pluralizes incorrectly. | Hard-code label map: country→Countries, province→Provinces, etc. | Small UI fix in HeirarchyListing.jsx filters. | P2 | Verified | TASK-097 | Filter plural map added (Countries, Provinces, Districts, Areas, Clusters). | 2026-04-15
BUG-12 | Bug | User UI | Profile picture uploader layout break | Label + uploader UI mis-aligned. | Flex/grid fix on the field container. | CreateUser/EditUser profile_picture block. | P2 | Verified | TASK-098 | Profile picture uploader now full-width bg-gray-50 border-gray-200 to match TextBox height. | 2026-04-15
BUG-15 | Bug | Hierarchy UI | Delete popup: long name overflows | Long hierarchy name breaks the confirm dialog layout. | max-w + truncate with title attr; or word-break. | ConfirmDialog: add overflow handling on entity name. | P2 | Wont Fix | TASK-099 | DeleteModal truncates long names with ellipsis + title tooltip. break-words on heading. | 2026-04-15
BUG-19 | Bug | UI | Table header shows white area sometimes | Header flicker / white patch under certain sorts. | Audit remaining DataTable sort/hover states; fix CSS inline-flex/whitespace. | Minor CSS polish. | P2 | Wont Fix | TASK-100 | DataTable Actions <th> gained text-white class. | 2026-04-15
BUG-25 | Bug | Role UI | Long description bolded inside delete popup | When description is long with ellipsis, delete confirm dialog renders it bold and styled. | Strip/escape markup, render as plain text; apply max-w+truncate. | ConfirmDialog: body text rendering. | P2 | Wont Fix | TASK-101 | DeleteModal strips HTML and renders plain text — no bold/markup leak. | 2026-04-15
BUG-33 | Bug | User | Email validation missing on frontend | Only server-side check. | yup email() schema on Create/Edit User. | Small schema addition. | P2 | Verified | TASK-102 | CreateUser + EditUser email regex check before submit. | 2026-04-15