## Project Plan
Web Portal
S.No | Items | Start Date | End Date | Working Days
1 | Database Design / Application Architecture / Auth Module | 2026-03-31 | 2026-04-03 | 4
2 | Heirarchy Management (Top to bottom heirarchy) | 2026-04-06 | 2026-04-09 | 4
3 | Role Management | 2026-04-10 | 2026-04-13 | 2
4 | User Management (Top to bottom heirarchy) | 2026-04-14 | 2026-04-16 | 3
| Staging Deployment for testing | 2026-04-17 | 2026-04-17 | 1
5 | Donor Management | 2026-04-20 | 2026-04-20 | 1
6 | Projects Management | 2026-04-21 | 2026-04-21 | 1
7 | Holidays Management (Top to bottom heirarchy) | 2026-04-22 | 2026-04-23 | 2
8 | Hybrid Heirarchy | 2026-04-24 | 2026-04-30 | 5
9 | School Management | 2026-05-04 | 2026-05-08 | 5
10 | Device Management | 2026-05-11 | 2026-05-11 | 1
11 | Profile Management | 2026-05-12 | 2026-05-12 | 1
12 | Shift Management | 2026-05-13 | 2026-05-13 | 1
| Staging Deployment for testing | 2026-05-14 | 2026-05-14 | 1
13 | Student Management | 2026-05-15 | 2026-05-19 | 3
14 | Attendance Listing Page | 2026-05-20 | 2026-05-25 | 4
| Staging Deployment, Testing and Bug Fixes | 2026-06-01 | 2026-06-02 | 2
15 | Logs Management (Activity Log, Change Log, Error logs) | 2026-06-03 | 2026-06-05 | 3
16 | Main Dashboard Changes | 2026-06-08 | 2026-06-10 | 3
| Staging Deployment, Testing and Bug Fixes | 2026-06-11 | 2026-06-11 | 1
17 | Project Management and Communication (Both Mobile and Web) | 2026-03-31 | 2026-06-11
| Total for Admin |  |  | 48
Mobile Application - Android
S.No | Items | Start Date | End Date | Working Days
1 | Fixes and Changes | 2026-06-12 | 2026-06-17 | 4
2 | Shifts listing | 2026-06-18 | 2026-06-18 | 1
3 | User Sync Funtionality | 2026-06-19 | 2026-06-19 | 1
4 | Guest login for student | 2026-06-22 | 2026-06-22 | 1
| Total for Mobile Application |  |  | 7
| Live Deployment, Final Testing,Review and Bug Fixes | 2026-06-23 | 2026-06-26 | 4
| Grand Total | Total Working Days |  | 59