## Summary
TTWF Bugs — UAT Test Scenarios (4-16-26)
Round 1 (previously fixed — verify): 14 items
Round 2 (newly reported): 13 items ¦ Round 3 (Apr 20): 7 items
Total: 34
How to use
1. Run through each item on the two sheets.
2. Pick a value in the Status column (dropdown).
3. Fill Actual result / Notes when something deviates.
4. Tester + Date for audit trail.
Status legend
Pass | Matches expected result
Fail | Does not match — log in notes
Blocked | Cannot execute right now
Partial | Works mostly — minor deviation
Skipped | Not applicable in this run
Live tally
Pass | 21
Fail | 3
Blocked | 0
Partial | 9
Skipped | 0

## Round 1 (Re-verify)
ID | Area | Description (from notes) | Steps to test | Expected result | Priority | Status | Actual result / Notes | Tester | Date
R1-01 | User Access | Access validation: when Country selected but province/district/area/cluster not, no error shown on Save Profile. Even with nothing selected, no error. | 1. Open Create/Edit User. 2. Toggle global access OFF. 3. Select only 1 country, nothing else. 4. Click Save. | Inline error under access section: 'Select at least one province.' (or next empty level). Auto-scroll to it. | P0 | Partial | region is not selected, but gives no error in user edit/create screen, In user edit screen, those region are also shown, whose provinces are not checked
R1-02 | Password | Password validation error message inconsistent across screens. Should show same rule-list message everywhere. | 1. Create user with weak password on Create User. 2. Change password on MyProfile with weak value. 3. Change password on forced-reset screen with weak value. | All three surfaces show the SAME concatenated rule-failure message (e.g. 'must be 8 chars. must contain uppercase.'). | P1 | Partial | Still shown the error based on validation, means if can't add special character then it tells atleast one special character, if not add capital letter, then tells alteast one capital, I want message remains same
R1-03 | Users BE | DB integrity error (employee_id duplicate) raised as 500 traceback instead of friendly 400. | 1. Create user with employee_id = 'EMP-015' (already used by deleted user). | 400 response with message 'A user with this employee ID already exists.' — no 500 traceback. | P0 | Pass
R1-04 | Roles Email | If role creator is also a checker, the creation email is sent to them too. | 1. Login as user who has BOTH roles.can_add AND role_checker.can_view. 2. Create a new role. 3. Check their own inbox. | Creator's own email is NOT in the recipient list. Other checkers receive the email. | P1 | Pass
R1-05 | Roles Email | On role UPDATE, checkers are not notified — should get email similar to create. Updater (if checker) excluded. | 1. Login as maker+checker user. 2. Edit an approved role and save. 3. Check OTHER checkers' inboxes. | Other checkers receive 'Role Updated — pending approval' email. Updater themselves do NOT receive it. | P1 | Pass
R1-06 | Roles Flow | Role status on update: listing must show 'Approved', approval queue shows 'Pending'. On overwriting a pending request, the old pending should still appear in Role History. | 1. Edit approved role → submit (status='pending'). 2. Verify Roles listing still shows 'Approved' for this role. 3. Verify Approval Queue shows this role as pending. 4. Edit the same role again (overwrite pending). 5. Check Role History tab — previous submission must appear (as superseded or rejected). | Listing = Approved. Queue = Pending. History shows BOTH the old and new submissions. | P0 | Pass
R1-07 | Roles History | Role History tab should NOT just show a table — there must be a view/review icon per row that opens a diff view (previous vs new permissions). | 1. Open Roles → Request History tab. 2. Click the view icon on any row. | Panel expands showing previous_payload vs payload side-by-side (or modal with diff). | P1 | Partial | In roles history tab, when no role shown in listing, select role dropdown works fine, but when select any role and listing shows the history, then dropdown options not shown properly, option select ke ander chup jaate hain, matlab pura dropdown sahi se nahin dikhta
R1-08 | Projects | Projects module has no add permission but Add button still visible/functional. | 1. Login as user without projects.can_add. 2. Open /projects listing. | 'Add Project' button hidden. Direct navigation to /create_project redirects to first accessible route. | P0 | Pass
R1-09 | Hierarchy Region | When no province selected in Create Region, error says 'At least one district required' — should say 'province'. Mandatory fields also need * asterisk. | 1. Create Region with no province/district selected. 2. Submit. | Error: 'At least one province must be assigned' (not district). Countries/Provinces/Districts column headers have red * marker. | P1 | Fail | In region creation, now distrcit is removed, only country and city is mandatory so update the validations message accordingly and also show message when country is also not selected
R1-10 | Edit User | User A (more access) edits User B (less access): B's assigned items should be ticked; A's extra items shown unchecked (so A can assign); items B has that A doesn't — NOT shown. | 1. LI user with Sindh+Punjab access edits EU with only Sindh. 2. Open EU's edit page. | Sindh = checked, Punjab = unchecked (available for LI to tick). Any province EU has that LI doesn't = not visible. | P1 | Partial | Good, access level related approach is right, if user B has no access of those in which user A has, so User B can't view those, this works fine, but one thing, I view that child shows those heirarchy memebers also in edit user, in which parent is not checked, child only shows those when parent is checked, same occurs in region also and point it above, clearify this also before working on this
R1-11 | Users UI | Long Designation in user listing overflows — should truncate with ellipsis. | 1. Create user with Designation = 40+ characters. 2. View in Users listing. | Designation truncated at ~25 chars with '...'. Full value shown in title tooltip on hover. | P2 | Pass
R1-12 | MyProfile | Password set via MyProfile — no success message shown. | 1. MyProfile → fill new+confirm password. 2. Save. | Green success toast: 'Profile & password updated successfully!' | P1 | Pass
R1-13 | Edit User | Faisal (no global) viewing Sagar (global access) in Edit User sees hierarchy levels NOT assigned to Faisal (only country hidden correctly, rest leaks). | 1. Login as Faisal (limited access). 2. Open Edit User for Sagar. | Only Faisal's accessible hierarchy items shown — Sagar's global access does NOT expose Faisal to items outside Faisal's scope. | P0 | Pass
R1-14 | Hierarchy Edit UI | Long country name in Hierarchy Edit dropdown hides edit/delete icons next to selector. | 1. Create a country with a very long name. 2. Open Edit Hierarchy → select that country. | Country label truncates with ellipsis. Edit/Delete buttons remain visible (shrink-0). | P2 | Partial | On Update country, dropdown still shows previous name, not the updated one

## Round 2 (New)
ID | Area | Description (from notes) | Steps to test | Expected result | Priority | Status | Actual result / Notes | Tester | Date
R2-01 | Profile UI | Profile Picture UI in Profile section not looking good. | 1. Open MyProfile. 2. Look at the Profile Picture section layout. | Uploader is full-width and aligned consistently with other form fields (bg-gray-50, border-gray-200, py-3). | P2 | Pass
R2-02 | Roles UI | Roles Create/Edit screen: on validation error, page does not scroll to the first invalid field. | 1. Open Create Role. 2. Leave Name empty and click Save. | Page auto-scrolls up to the Name field and it receives focus. | P1 | Pass
R2-03 | Users Listing | User A and B have same access at Area level, but cluster A for User A, cluster B for User B. User A (LI) should NOT see User B in user listing (because cluster access doesn't overlap). | 1. LI user with Cluster A access opens Users listing. 2. Verify only users sharing at least one cluster with LI are visible. | User B (cluster B only) is NOT in the listing. Super-admin / global access sees all. | P0 | Partial | User A has access of Cluster A and Cluster B both, and user B has only access of cluster A, user B can't view user A is listing, but user C has access of cluster B, he is able to view User A, why this behavious occurs, as user B can also view user A, because they have same access in any level
R2-04 | Password | Last 3 used passwords must be blocked on any password-change flow. Count is configurable in backend settings. | 1. Change password to 'Abc@1234'. 2. Change again to 'Xyz@1234'. 3. Change again to 'Mno@1234'. 4. Try to set it back to 'Abc@1234'. | Error: 'Cannot reuse one of your last 3 passwords.' settings.PASSWORD_HISTORY_COUNT controls the count. | P1 | Pass
R2-05 | Routing | Unknown URL (anything after / that doesn't match a route) should redirect to first accessible screen, not show blank. | 1. Logged in → navigate to /random-invalid-path. | Redirected to first accessible route (or dashboard/my_profile fallback). | P1 | Pass
R2-06 | Users Email | On user creation email, login URL must be included and dynamically derived from settings (not hardcoded), so deployment domain changes don't break it. | 1. Create a new user. 2. Check recipient's inbox. | Email body contains login URL constructed from settings.SERVER_ADDR. URL matches current deployment host. | P1 | Pass
R2-07 | User Access | Region in access level: if a region spans multiple districts, it was shown multiple times. Must deduplicate — one region per entry. | 1. Create/Edit user with a province whose region is mapped to 3 districts. 2. Observe Region column in access level. | Region appears ONCE. Districts listed as sub-text under the region name. | P1 | Not Run | Region creation gives district error
R2-08 | Edit User Perf | Edit User screen makes too many API calls on open (see screenshot Edit API Calls.png). | 1. Open Edit User. 2. Open Network tab. | At most ~4 calls: /users/{id}/edit-context/ (merged), /master/countries/, /roles/, (plus avatar). No cascading per-level fetches. | P1 | Partial | 6 Calls, API's are 3 but call twice time
R2-09 | Tabs Perf | On screens with tabs (e.g. Roles), data for all tabs must NOT be fetched on mount. Lazy-load on tab switch. | 1. Open Roles page. 2. Network tab: confirm only Roles tab data loaded. 3. Click Approval Queue tab once. 4. Confirm Queue data fetched now. | Queue + History tab data fetched only on first tab click. | P1 | Partial | In Role request history page, new one created, calls three api's, API's are 2 but one calls 2 times and other one calls 1 times, is there is any need to those two calls, or I think one API can do my work
R2-10 | Phone Validation | Phone number validation should show a proper country-specific message on submit. | 1. Select Country = India. 2. Enter Pakistani mobile number. 3. Submit. | Error: 'Invalid phone number for IN.' (or 'Phone number is not valid for IN.'). | P1 | Fail | Selected country is United States, on wrong number getting this message "Invalid phone number for GB".
R2-11 | Users UI | 'Select Role' option in user creation dropdown must be disabled (can't be submitted). | 1. Open Create User. 2. Inspect Role select — placeholder option. | First option 'Select Role' has disabled attribute. Form cannot submit with it selected (validation blocks). | P2 | Pass
R2-12 | Tables UI | Table header still shows white area on Hierarchy and Users tables. Turns correct on hover. Remove white override CSS. | 1. Open Hierarchy listing. 2. Look at table header row without hovering. | Header background = primary color consistently. No white flash. | P2 | Pass
R2-13 | Roles UI | Delete Role confirmation popup: description with '...' appears highlighted/bold (only for descriptions containing ellipsis). Should be plain text. | 1. Delete a role whose description is >30 chars. 2. Observe popup body. | Name = bold, description = plain text (no highlight), truncated with title tooltip. | P2 | Fail | Still tooltip text appears on top of popup

## Round 3 (Apr 20)
ID | Area | Description (from notes) | Steps to test | Expected result | Priority | Status | Actual result / Notes | Tester | Date
R3-01 | Users Validation | Backend phone error returned as non_field_errors → frontend didn't show under Mobile field. Also no client-side phone validation. | 1. Create User. Select Country = India. Enter 0300 1234567 (PK format). 2. Click Save. | Inline error under Mobile Number: 'Invalid phone number for IN.' — both FE validation catches it, and if server returns non_field_errors with 'phone' keyword it maps to mobile_number field. | P0 | Pass
R3-02 | User Access UI | Regional access columns had empty spaces in the grid (row 2 — Cluster/School — was 4-col grid with 2 empty slots). Must use full width. | 1. Open Create or Edit User. 2. Scroll to Regional Access section. | Row 1: Country, Province, Region, Area (each 25% width). Row 2: Cluster, School (each 50% width). No empty/wasted slots. | P2 | Pass
R3-03 | Roles Listing | Approval Queue tab count badge only appears after clicking the tab. User wants the badge visible on mount so they know pending work exists. | 1. Login as checker. 2. Open /roles (Roles tab shown). 3. Look at 'Approval Queue' tab label without clicking. | Count badge visible next to Approval Queue label from the start — e.g. 'Approval Queue 3'. Achieved via a cheap count-only fetch on mount (page_size=1 + count from response). | P1 | Pass
R3-04 | Role History UX | Request History view icon opened diff INLINE below the row. User wants a Modal similar to Review Role page with previous vs new permissions side-by-side. Also modules shown as 'Module 1, Module 2' — must show readable module names. | 1. Open Roles → Request History tab. 2. Pick a role. 3. Click the view/diff icon on any row. | Modal opens centered. Left panel = Previous (red tint), right panel = Proposed (green tint). Each panel shows role name, description, and a table of module-name + View/Add/Edit/Delete ticks. | P1 | Pass
R3-05 | Role Status | If a role was approved and then someone edited it (pending update), Approval Queue tab showed it as 'Approved' — confusing. Must show 'Pending' in the queue listing. | 1. Approve a role. 2. Edit it (creates a pending request). 3. Open Approval Queue tab. | Role status badge in queue shows 'Pending' (not 'Approved'). Main Roles listing still shows 'Approved' (since role.approval_status stays at its last-approved state). | P1 | Pass
R3-06 | Request History Filter | Select component's placeholder option ('Select a role') was hard-disabled — user couldn't return to the empty-state once a role was picked. | 1. Request History tab → pick a role → view history. 2. Reopen the role select. 3. Try to pick 'Select a role' again to reset. | Empty option is selectable on optional filters (required forms still keep it disabled). After selecting, the list returns to 'Select a role to view its request history.' | P2 | Partial | I think you wrong understood it, UI principles I think not recommend this, tell me also, I want it not selects again
R3-07 | Role Request Supersession | When a pending request is edited again (overwritten), the old request was being marked as 'rejected' with remarks 'Superseded by newer submission'. User wants it to remain labelled as 'pending' in history (factually it was pending when submitted); use a separate 'is_active' flag instead. | 1. Edit an approved role (creates pending request P1). 2. Before P1 is reviewed, edit the role again (creates P2). 3. Open Request History. | P1 shows status 'Pending' (not Rejected) with remarks 'Superseded by newer submission'. P2 still visible in Approval Queue. Approve/reject only operates on P2. | P1 | Pass

## Errors and Bugs
Name | Description
Role Update | If no change in role, not create requests
User delete | Cannot delete only user in system
User Listing | User has both Cluster A and Cluster B access, when I unchecked the Cluster B and save user, it still shows Cluster B in access level
Create User | Calls 6 API's, API's are only two countries and roles, countries calls 4 times and roles calls 2 times, also tell me if there are 100 roles in system, how they are call

## Claude Fixes - Apr 22
TTWF Portal — Claude Code Fixes & Outstanding Issues ¦ Session: Apr 21-22, 2026
Ref ID | Source | Area | Bug / Issue | Your Actual Result / Notes | Fix Applied by Claude | Fix Status | Priority | Verification Notes
Errors and Bugs Tab
EB-01 | Errors & Bugs | Roles | Role Update: if no change in role, should not create a new request | If no change in role, not create requests | Added no-op detection in EditRole using useRef snapshot. If name, description and all permissions unchanged, shows warning 'No changes to save.' and skips the API call. | Fixed - Verify | High | Fixed
EB-02 | Errors & Bugs | Users | User delete: cannot delete the only user in the system | Cannot delete only user in system | Added guard in UserViewSet.destroy(): counts active profiles; returns HTTP 400 'Cannot delete the only remaining user in the system.' when count <= 1. | Fixed - Verify | High | Fixed
EB-03 | Errors & Bugs | User Access | User Listing: unchecked Cluster B still shows in access level after save | User has both Cluster A and Cluster B access, when I unchecked Cluster B and save, it still shows Cluster B in access level | Fixed _set_regional_access in serializers.py: stale queryset reuse caused incomplete deletes. Now uses fresh PivotModel.objects.filter() per delete. Also fixed li_profile=None silent no-op path. | Fixed - Verify | High | Fixed
EB-04 | Errors & Bugs | Users Perf | Create User calls 6 APIs — countries calls 4x, roles calls 2x | Calls 6 APIs, API's are only two (countries and roles), countries calls 4 times and roles calls 2 times | Fixed excessive API calls on Create User and Edit User: consolidated fetches, removed duplicate dispatches on mount and filter changes. | Fixed - Verify | Medium | Still countries(heiararchy) and countries (all) both call twice time, is this only happens in debug? Will check in staging site after running build
Round 1 (Re-verify) — Items with Actual Result / Notes
R1-01 | Round 1 | User Access | Access validation: region shown in Edit User even when parent province is not checked | Region is not selected, but gives no error in user edit/create screen. In user edit screen, those regions are also shown whose provinces are not checked. | Fixed child-items showing without parent checked (TASK-016). Hierarchy and Edit User now only show children when parent is selected/checked. | Fixed - Verify | P0 | Fixed
R1-02 | Round 1 | Password | Password validation message inconsistent — should show all rules at once regardless of which rule fails | Still shown the error based on validation — if can't add special character it tells that, if no capital then tells that. I want message remains the same (all rules listed). | Fixed password validation to show all failing rules at once instead of single rule per submit (TASK-018). Same consolidated message shown on Create User, MyProfile, and forced-reset screens. | Fixed - Verify | P1 | Fixed
R1-07 | Round 1 | Roles History | Role history tab: when a role is selected and listing shows, dropdown options are hidden behind the table | In roles history tab, when no role shown in listing, select role dropdown works fine, but when select any role and listing shows the history, then dropdown options not shown properly — option select ke andar chup jaate hain, matlab pura dropdown sahi se nahin dikhta. | Fixed role history dropdown z-index: dropdown was hidden behind the listing table. Applied z-index fix so dropdown renders above table rows (TASK-020). | Fixed - Verify | P1 | Fixed
R1-09 | Round 1 | Hierarchy Region | Region creation: district removed but error messages not updated; no error when country also not selected | In region creation, now district is removed, only country and city is mandatory so update the validation messages accordingly and also show message when country is also not selected. | Not addressed in this session — validation messages and missing-country error for region creation are still outstanding. | Open - Not Yet Done | P1 | Fixed
R1-10 | Round 1 | Edit User | Child hierarchy items shown in Edit User even when parent is not checked | Child shows those hierarchy members also in edit user in which parent is not checked. Child only shows those when parent is checked. Same occurs in region also. | Fixed child-items showing without parent checked (TASK-016). Children are now only displayed/selectable when their parent is checked. | Fixed - Verify | P1 | Fixed
R1-14 | Round 1 | Hierarchy Edit UI | Country dropdown in Edit Hierarchy still shows old name after update | On Update country, dropdown still shows previous name, not the updated one. | Fixed country dropdown showing old name after update (TASK-021). Dropdown now reflects the updated name immediately after save. | Fixed - Verify | P2 | Fixed
Round 2 (New) — Items with Actual Result / Notes
R2-03 | Round 2 | Users Listing | User visibility: User B (cluster A only) cannot see User A (cluster A+B) — should be able to since they share cluster A | User A has access of Cluster A and Cluster B both, and User B has only access of Cluster A. User B can't view User A in listing, but User C who has access of Cluster B can view User A. User B should also view User A because they have same access in any level. | Fixed shared cluster access visibility logic (TASK-017). Users sharing at least one cluster/area/region now correctly see each other in the listing. | Fixed - Verify | P0 | Fixed
R2-07 | Round 2 | User Access | Region column in access level: region spanning multiple districts was shown multiple times | Region creation gives district error — could not run this test. | Region deduplication was fixed in CascadingAccessColumn (TASK-128 / earlier fix). However R1-09 region creation error is still open and may be blocking this test. | Partially Fixed | P1 | Fixed
R2-08 | Round 2 | Edit User Perf | Edit User screen makes too many API calls on open | 6 Calls — APIs are 3 but each calls twice. | Fixed excessive API calls on Edit User (TASK-022). Consolidated fetches, removed duplicate dispatches. Should now be at most 3 unique calls. | Fixed - Verify | P1 | Still countries and edit context both call twice time, is this only happens in debug? Will need to check on production build too
R2-09 | Round 2 | Roles Tabs Perf | Role request history page: duplicate API calls on tab open | In Role request history page, new one created, calls three APIs — one API calls 2 times and another calls 1 time. | Fixed duplicate API calls on Role request history page (TASK-023). Calls are now deduplicated. | Fixed - Verify | P1 | Fixed
R2-10 | Round 2 | Phone Validation | Phone validation shows wrong country code — showing GB instead of selected country | Selected country is United States, on wrong number getting this message 'Invalid phone number for GB'. | Fixed phone validation to use the selected country code (TASK-024). Message now shows correct country e.g. 'Invalid phone number for US.' | Fixed - Verify | P1 | We need to remove the country based validation and also no need to show format of phone number, Validation will be allow only digits and max length is the maximum limit of phone number allowed by any country, first tell me which country has highest length of number
R2-13 | Round 2 | Roles UI | Delete Role confirmation popup: tooltip text renders on top of the popup | Still tooltip text appears on top of popup. | Fixed tooltip appearing above modal/popup (TASK-019/025). Raised Modal z-index to z-[9999999] so it always renders above Tooltip's inline zIndex:999999. | Fixed - Verify | P2 | Fixed
Round 3 (Apr 20) — Items with Actual Result / Notes
R3-06 | Round 3 | Roles History Filter | Select placeholder in Request History filter: user could not re-select empty option after picking a role | I think you wrong understood it. UI principles I think not recommend this. I want it not selects again. | Fixed Select component: placeholder is now disabled after first selection so user cannot accidentally go back to empty state (TASK-019). This matches the user's intent. | Fixed - Verify | P2 | Fixed
Legend: Green = Fixed - update to 'Verified' after QA ¦ Yellow = Partially Fixed - needs retest ¦ Orange = Open - not yet addressed this session ¦ Verification Notes column: fill in your observations

## 29-Apr-26 Holiday
29-Apr-26 Holiday Management — Test Cases
No. | Module | Test Case | Steps | Expected Result | Actual Result | Status | Notes | Priority
SECTION 1: CREATE HOLIDAY
HC-001 | Create Holiday | Create holiday with valid data | 1. Go to Holidays > Create Holiday 2. Enter calendar name 3. Select hierarchy level 4. Add a holiday entry with future start/end dates 5. Click Save | Holiday calendar created successfully. Redirected to Holidays list. New calendar appears in list. |  | pass |  | High
HC-002 | Create Holiday | Calendar name — allowed special characters | 1. Enter a name with allowed chars: "Eid-Ul-Fitr (2026) & Eid'l Adha" 2. Fill rest of form 3. Click Save | Calendar saved successfully. Allowed chars: letters, digits, spaces, - ' . , () / & |  | pass |  | High
HC-003 | Create Holiday | Calendar name — disallowed special characters | 1. Enter a name with disallowed chars e.g. "Eid@2026!" 2. Click Save | Validation error shown below Calendar Name field: "Calendar name contains invalid characters." |  | pass |  | High
HC-004 | Create Holiday | Calendar name — auto title-case | 1. Type calendar name all lowercase: "national holidays" 2. Observe field value | Each word capitalised as typed: "National Holidays" |  | pass |  | Medium
HC-005 | Create Holiday | Calendar name — blank not allowed | 1. Leave calendar name empty 2. Click Save | Error shown: "Calendar name is required." |  | pass |  | High
HC-006 | Create Holiday | Calendar name — max length 200 chars | 1. Paste 201-character string into calendar name 2. Click Save | Input truncated to 200 characters (maxLength attribute) |  | pass |  | Low
HC-007 | Create Holiday | Hierarchy selection required | 1. Leave hierarchy empty (no level selected) 2. Fill rest and click Save | Error below hierarchy: "Please select at least one hierarchy level." |  | pass |  | High
HC-008 | Create Holiday | Hierarchy — All placeholder labels | 1. Open Create Holiday 2. Observe dropdown placeholders | Dropdowns show "All Countries", "All Provinces", etc. (not "Select Country") |  | pass |  | Medium
HC-009 | Create Holiday | Holiday entry — past start date blocked | 1. Enter a start date in the past (e.g. 2026-01-01) 2. Click Save | Error below Start Date: "Start date cannot be in the past." |  | pass |  | High
HC-010 | Create Holiday | Holiday entry — end date before start date | 1. Set start_date = 2026-06-01, end_date = 2026-05-30 2. Click Save | Error below End Date: "End date cannot be before start date." |  | pass |  | High
HC-011 | Create Holiday | Holiday entry — holiday name blank | 1. Leave holiday entry name empty 2. Fill dates 3. Click Save | Error below Holiday Name: "Holiday name is required." |  | pass |  | High
HC-012 | Create Holiday | Holiday entry — duplicate (same name + dates) | 1. Add two entries with same name "Eid" and same start/end dates 2. Click Save | Error: "Duplicate holiday with the same name and dates." |  | pass |  | High
HC-013 | Create Holiday | Duplicate calendar name — same level + overlapping dates | 1. Create calendar "National Calendar" for Pakistan, June 2026 2. Try to create another "national calendar" (lowercase) for Pakistan, May–July 2026 3. Click Save | Backend error shown in appropriate field: "A calendar with this name already exists for Pakistan (Country level) and overlapping date range." |  | pass | Same name pe same year validation lagani ha nake date range per | High
HC-014 | Create Holiday | Same name at different levels allowed | 1. Create "School Calendar" for Country = Pakistan 2. Create "School Calendar" for Province = Sindh 3. Observe | Both created successfully — different level, so no uniqueness conflict |  | pass |  | Medium
HC-015 | Create Holiday | Add multiple holiday entries | 1. Click "+ Add Holiday" to add 3 entries 2. Fill all with valid future dates 3. Click Save | All 3 entries saved and visible on detail/edit page |  | pass |  | Medium
HC-016 | Create Holiday | Remove a holiday entry | 1. Add 2 entries 2. Click delete icon on the second entry 3. Click Save | Second entry removed; form saves with only 1 entry |  | pass |  | Medium
HC-017 | Create Holiday | Recurring holiday — set is_recurring + days_offset | 1. Add holiday entry, check "Repeat every year" 2. Set Days Offset to -3 3. Save | Calendar saved. Entry has is_recurring=true and days_offset=-3 |  | pass |  | Medium
HC-018 | Create Holiday | School level — create calendar at school level | 1. Select Country > Province > Area > Cluster > School 2. Fill calendar name and entries 3. Save | Calendar created at school level. assigned_level=school in backend. |  | pass |  | High
SECTION 2: EDIT HOLIDAY
HE-001 | Edit Holiday | Edit calendar name and save | 1. Open Holidays list 2. Click Edit on any calendar 3. Change calendar name 4. Click Update Holiday | Calendar name updated. Success message shown. Redirected to list. |  | pass |  | High
HE-002 | Edit Holiday | Past holiday entries shown as locked | 1. Open edit for a calendar that has entries with end_date in the past 2. Observe those entries | Past entries have "Passed" badge, all fields disabled (greyed out), no delete button |  | pass |  | High
HE-003 | Edit Holiday | Cannot set past start date on non-past entry | 1. Edit a calendar 2. On a non-past entry change start_date to a past date 3. Click Update | Error below Start Date: "Start date cannot be in the past." |  | pass |  | High
HE-004 | Edit Holiday | Add new entry to existing calendar | 1. Edit a calendar 2. Click "+ Add Holiday" 3. Fill new entry with future date 4. Click Update | New entry added and saved. Calendar now has additional entry. |  | pass |  | Medium
HE-005 | Edit Holiday | Delete a non-past entry from calendar | 1. Edit calendar with 2+ non-past entries 2. Click delete icon on one entry 3. Click Update | Entry removed. Calendar updated with remaining entries. |  | pass |  | Medium
HE-006 | Edit Holiday | Past entries preserved after update | 1. Edit calendar that has past entries 2. Modify a non-past entry 3. Click Update 4. Re-open edit page | Past entries still present and unchanged. Only non-past entries were updated. |  | pass |  | High
HE-007 | Edit Holiday | Change hierarchy level | 1. Edit a calendar 2. Change hierarchy from Country to Province 3. Click Update | Calendar updated with new hierarchy assignment. |  | pass |  | Medium
HE-008 | Edit Holiday | Duplicate entry check on update | 1. Edit calendar 2. Add duplicate entry (same name + dates as existing non-past entry) 3. Click Update | Error: "Duplicate holiday with the same name and dates." |  | pass |  | High
HE-009 | Edit Holiday | Initial hierarchy pre-populated | 1. Open edit for an existing calendar 2. Observe hierarchy dropdowns | Dropdowns pre-filled with the calendar's current hierarchy (country, province, area, cluster, school as applicable) |  | pass |  | High
HE-010 | Edit Holiday | Status change from active to inactive | 1. Edit a calendar 2. Change status to "Inactive" 3. Update | Status updated. Calendar shows "Inactive" in list. |  | pass |  | Medium
SECTION 3: DELETE HOLIDAY
HD-001 | Delete Holiday | Delete calendar with no past entries | 1. Open Holidays list 2. Find a calendar with only future entries 3. Click Delete > Confirm | Calendar deleted. No longer in list. |  | pass |  | High
HD-002 | Delete Holiday | Delete blocked — calendar has past entries | 1. Open Holidays list 2. Find calendar with at least one past holiday entry 3. Observe delete icon | Delete icon is greyed out (disabled). Tooltip: "Cannot delete: this calendar contains past holiday entries" |  | pass |  | High
HD-003 | Delete Holiday | Delete blocked — server-side protection | 1. Attempt DELETE via Postman or API call on calendar with past entries (bypass frontend) | API returns 400: "Cannot delete a calendar that contains past holiday entries." |  | pass |  | High
HD-004 | Delete Holiday | Cancel delete confirmation | 1. Click Delete on a deletable calendar 2. In confirmation dialog click Cancel | Calendar not deleted. Still in list. |  | pass |  | Medium
SECTION 4: HOLIDAYS LIST & FILTERS
HL-001 | Holidays List | List shows all calendars with correct columns | 1. Open Holidays page 2. Observe columns | Columns: Name, Status, Assigned Level, Assigned To, No. of Holidays, Start Date, End Date, Actions |  | pass |  | High
HL-002 | Holidays List | Filter by hierarchy level | 1. In filter section select Country = Pakistan 2. Observe list | Only calendars assigned to Pakistan (country level) appear |  | pass |  | High
HL-003 | Holidays List | Filter clears with Clear button | 1. Apply a hierarchy filter 2. Click Clear 3. Observe list | All calendars shown again. Dropdowns reset to "All X". |  | pass |  | Medium
HL-004 | Holidays List | Filter by school level | 1. Select all the way down to a school 2. Apply filter | Only calendars assigned to that specific school appear |  | pass |  | High
HL-005 | Holidays List | Pagination works | 1. Create enough calendars to fill 2 pages 2. Navigate to page 2 | Page 2 shows next set of calendars. Pagination controls work. |  | pass |  | Medium
HL-006 | Holidays List | Assigned To column shows entity name | 1. View holiday assigned to a Province 2. Check Assigned To column | Shows province name (e.g. "Sindh"), not ID |  | pass |  | Medium
HL-007 | Holidays List | has_past_entries disables delete icon | 1. Calendar A has all future entries → delete icon active (red) 2. Calendar B has at least 1 past entry → delete icon grey/disabled | Correct icon state for each calendar |  | pass |  | High
SECTION 5: RECURRING HOLIDAY CRON
HR-001 | Recurring Cron | Dry run — preview without creating | Run: python manage.py generate_recurring_holidays --year 2027 --dry-run | Output shows [WOULD CREATE] entries with adjusted dates. No records created in DB. |  | Pending |  | High
HR-002 | Recurring Cron | Generates calendar for target year | 1. Ensure calendar "National Calendar" 2026 has recurring entries 2. Run: python manage.py generate_recurring_holidays --year 2027 | "National Calendar 2027" created with same recurring entries, dates advanced by 1 year. |  | Pending |  | High
HR-003 | Recurring Cron | Non-recurring entries not carried over | 1. Calendar has mix: 1 recurring + 1 non-recurring entry 2. Run cron for next year | Only the recurring entry appears in new calendar. Non-recurring entry not copied. |  | Pending |  | High
HR-004 | Recurring Cron | Idempotent — safe to run twice | 1. Run cron for year 2027 2. Run cron again for year 2027 | Second run skips: "[SKIP] 'National Calendar 2027' already exists". No duplicate created. |  | Pending |  | High
HR-005 | Recurring Cron | Days offset applied correctly | 1. Holiday on 2026-05-26 with days_offset = -3 2. Run cron for 2027 | New entry start_date = 2027-05-23 (26 May - 3 days) |  | Pending |  | High
HR-006 | Recurring Cron | Zero offset — same date next year | 1. Holiday on 2026-08-14 with days_offset = 0 2. Run cron for 2027 | New entry start_date = 2027-08-14 |  | Pending |  | Medium
HR-007 | Recurring Cron | Year stripped from name before appending | 1. Calendar named "National Calendar 2026" has recurring entries 2. Run cron --year 2027 | New calendar named "National Calendar 2027" (not "National Calendar 2026 2027") |  | Pending |  | High
HR-008 | Recurring Cron | Feb 29 → Feb 28 in non-leap year | 1. Holiday on 2024-02-29 (leap year), is_recurring 2. Run cron for 2025 (non-leap) | New entry date is 2025-02-28 (graceful fallback) |  | Pending |  | Medium
HR-009 | Recurring Cron | No source year entries — skips gracefully | Run cron for a year where no calendars have recurring entries from previous year | Output: "No calendars found with recurring entries from YYYY." Command exits cleanly. |  | Pending |  | Medium
HR-010 | Recurring Cron | Default year = current year | Run: python manage.py generate_recurring_holidays (no --year arg) | Uses today's year as target year automatically. Source = target - 1. |  | Pending |  | Medium
SECTION 6: FIELD VALIDATION EDGE CASES
HV-001 | Validation | Same name different case is duplicate | 1. Create "National Calendar" for Pakistan, June 2026 2. Try create "NATIONAL CALENDAR" for Pakistan, May–July 2026 | Rejected as duplicate (case-insensitive match) |  | Pending |  | High
HV-002 | Validation | Same name non-overlapping dates allowed | 1. Create "Annual Calendar" for Pakistan, Jan–Jun 2026 2. Create "Annual Calendar" for Pakistan, Jul–Dec 2026 | Both created successfully (non-overlapping date ranges) |  | Pending |  | Medium
HV-003 | Validation | Backend error routing — field errors inline | 1. Submit form with server-side field error (e.g. duplicate name) 2. Observe error display | Name error shown below Calendar Name field (not in toast) |  | Pending |  | High
HV-004 | Validation | Backend error routing — non-field errors in toast | 1. Trigger a non-field backend error 2. Observe display | Error shown as red toast notification at bottom of screen |  | Pending |  | High
HV-005 | Validation | Error messages capitalised | 1. Trigger any backend validation error 2. Observe first letter of error message | First letter of every error message is capitalised before display |  | Pending |  | Medium
HV-006 | Validation | Days offset accepts negative numbers | 1. Set days_offset to -5 2. Save | Saved with days_offset = -5. No validation error. |  | Pending |  | Medium
HV-007 | Validation | Days offset defaults to 0 | 1. Leave days_offset empty 2. Save | days_offset saved as 0 (parseInt fallback) |  | Pending |  | Low